## Sprint_1
Sprint 1
ID	As a…	I want to be able to…	So that I can…	Tasks to be Completed	Member	Status
1	User	Open an mp3	edit it and play it back	Add file browser to GUI	Jonathan Brownlee, William Young	Complete
				Add action event for open	Jonathan Brownlee, William Young	Complete
2	User	Play an mp3 back	hear what I’m working with	Add play, pause, and stop buttons	Jonathan Brownlee, William Young	Complete
				Add play action event	Jonathan Brownlee, William Young	Complete
				Add pause action event	Jonathan Brownlee, William Young	Complete
	User			Add stop action event	Jonathan Brownlee, William Young	Complete
3	User	Close a file	cease using it for my project	Add close file menuitem to GUI	Jonathan Brownlee, William Young	Complete
				Add close file action event	Jonathan Brownlee, William Young	Complete
4	User	see the song that is playing	keep track of what is open	Add panel to see mp3 file that is open	Dylan Ortiz	Complete

Sprint 2
ID	As a…	I want to be able to…	So that I can…	Tasks to be Completed	Member	Status
	Programmer	Code in JavaFX	Make modern GUI elements	Convert Swing to GUI	Jonathan Brownlee, William Young	Complete
	User	Access the source Github	See where this orogram came from	Add link to Github page	Dylan Ortiz	Complete
	USer	Have musical aid	Record music properly	Create a virtual metronome	Leo Crespo	Code skeleton done
				Add beat maker	Leo Crespo	Code skeleton done
				Add waveform for the songs	Morgan Cole	In progress
				Add timeline for audio	Dylan Ortiz	In progress

Sprint 3
ID	As a…	I want to be able to…	So that I can…	Tasks to be Completed	Member	Status

## Sprint_2
User Story	Tasks to be Completed	Member	Week 1		Week 2		Week 3		Week 4

## Sprint_3
User Story	Tasks to be Completed	Member	Week 1		Week 2		Week 3		Week 4