## Sprint_1
Sprint 1
ID	As a…	I want to be able to…	So that I can…	Tasks to be Completed	Member	Status
1	User	Open an mp3	edit it and play it back	Add file browser to GUI	Jonathan Brownlee, William Young	Complete
				Add action event for open	Jonathan Brownlee, William Young	Complete
2	User	Play an mp3 back	hear what I’m working with	Add play, pause, and stop buttons	Jonathan Brownlee, William Young	Complete
				Add play action event	Jonathan Brownlee, William Young	Complete
				Add pause action event	Jonathan Brownlee, William Young	Complete
				Add stop action event	Jonathan Brownlee, William Young	Complete
3	User	Close a file	cease using it for my project	Add close file menuitem to GUI	Jonathan Brownlee, William Young	Complete
				Add close file action event	Jonathan Brownlee, William Young	Complete
4	User	see the song that is playing	keep track of what is open	Add panel to see mp3 file that is open	Dylan Ortiz	Complete

Sprint 2
ID	As a…	I want to be able to…	So that I can…	Tasks to be Completed	Member	Status
	Programmer	Code in JavaFX	Make modern GUI elements	Convert Swing to GUI	Jonathan Brownlee, William Young	Complete
	User	Access the source Github	See where this orogram came from	Add link to Github page	Dylan Ortiz	Complete
	User	Have musical aid	Record music properly	Create a virtual metronome	Leo Crespo	Code skeleton done
	User	Easily sequence sounds	Make groovy rhythms	Add beat maker	Leo Crespo	Code skeleton done
	User	See the waveforms of the sounds	Tell where each track gets loud and soft	Add waveform for the songs	Morgan Cole	In progress
	User	See the order of my tracks	Arrange them in a way that sounds good	Add timeline for audio	Dylan Ortiz	In progress

Sprint 3
ID	As a…	I want to be able to…	So that I can…	Tasks to be Completed	Member	Status
	User	edit a beat once it is done	make changes if I want	Add button for editing beats	Jonathan Brownlee	Complete
				Add button to open MIDI file	Jonathan Brownlee	Complete
				Enable editing of beats	Jonathan Brownlee	In progress
	User	edit a synth once it is done	make changes if I want	Add button for editing synths	Jonathan Brownlee	Complete
				Add button to open MIDI file	Jonathan Brownlee	Complete
				Enable editing of synths	Jonathan Brownlee	In progress
	User	Add beats to my open files	Create new music	Add beat addition to left side of the pane	Will Young	Complete
			Modify a beat to my liking	Add drag and drop feature to the beats	Will Young	Complete
			Make a new beat along with other open files	Drag and drop new beat and edit on the fly
	User	record my synthesizer	produce music	Enable recording of synth	Jonathan Brownlee	Complete
	User	play my synth recordings back	hear what I’m working on	Enable playback of recording	Jonathan Brownlee	Complete
	User	save my work to a file	save it for later or share it	Add save beat as mid feature	Jonathan Brownlee	Complete
				Add save synth as midi feature	Jonathan Brownlee	Complete
	User	play a synthesizer	produce music	Code synthesizer	Leo Crespo	Complete

## Sprint_2
User Story	Tasks to be Completed	Member	Week 1		Week 2		Week 3		Week 4

## Sprint_3
User Story	Tasks to be Completed	Member	Week 1		Week 2		Week 3		Week 4